## Problem_Definition
Element | Case Study Content
Problem Description | Telecommunications customers may discontinue their subscriptions without being identified early. The project uses historical service, contract, and billing data to create a proof-of-concept churn-risk decision-support application.
Target Users and Stakeholders | Customer Retention Manager; Customer Service Supervisor; Business Manager; Data Science Team; IT and DataOps Team.
Expected Business Value | Prioritize retention work, support more focused customer interventions, reduce unnecessary campaign effort, and provide a repeatable view of churn patterns.
Why the Problem Is Important | Churn can affect recurring revenue and may require costly customer replacement. Earlier risk information supports more proactive and targeted decision-making.

## User_Stories
Story ID | User Story | Acceptance Criteria
US1 | As a Customer Retention Manager, I want a ranked list of customers by churn risk so that I can prioritize retention activities. | Customer ID displayed; churn probability displayed; Low, Medium, or High risk shown; table sortable; output exportable to CSV.
US2 | As a Customer Service Supervisor, I want to view the main factors associated with each high-risk customer so that agents can select a suitable intervention. | Two or three observed risk factors displayed; explanations written in non-technical language; filtering available by contract and tenure group.
US3 | As a Business Manager, I want a summary of churn patterns by customer segment so that I can allocate retention resources more effectively. | Overall churn rate displayed; segment counts and churn rates shown; at least two exploratory charts included; dataset execution date displayed.

## Product_Backlog
Backlog ID | Priority | Feature | Description | Related Story | Planned Sprint
PB1 | High | Dataset acquisition and documentation | Preserve the raw Kaggle data and document its source. | All | Sprint 1
PB2 | High | Data-quality checks | Check missing values, blanks, duplicates, types, and invalid values. | All | Sprint 1
PB3 | High | Cleaned customer dataset | Create reusable CSV and Excel outputs. | All | Sprint 1
PB4 | High | Churn segment summary | Calculate historical churn patterns by key segments. | US3 | Sprint 1
PB5 | High | Feature engineering | Create tenure, service, contract, payment, and support features. | US1; US2 | Sprint 2
PB6 | High | Baseline churn model | Build a class-weighted logistic-regression model. | US1 | Sprint 2
PB7 | High | Initial customer risk table | Show probability and Low, Medium, or High risk. | US1 | Sprint 2
PB8 | High | Model evaluation | Evaluate precision, recall, F1, ROC-AUC, and confusion matrices. | US1 | Sprint 3
PB9 | Medium | Churn-driver explanation | Show model importance and understandable observed risk factors. | US2 | Sprint 3
PB10 | Medium | Streamlit prototype | Create a simple internal decision-support interface. | US1-US3 | Sprint 3
PB11 | Medium | CSV export | Allow the filtered customer-risk list to be downloaded. | US1 | Sprint 3
PB12 | Low | Automated weekly scoring | Propose a scheduled batch-scoring process. | US1 | Sprint 4
PB13 | Low | Monitoring and drift checks | Plan data quality, performance, and distribution monitoring. | All | Sprint 4
PB14 | Low | Automatic alerts | Consider notifications in a future release after validation. | US1 | Future

## MVP_Definition
Sprint | MVP | Why Selected | Value Created
Sprint 1 | Cleaned CSV and Excel dataset, data dictionary, quality report, churn summaries, exploratory charts, and findings. | Reliable, understandable data is required before model development and provides immediate descriptive value. | Stakeholders can review historical churn patterns and confirm which customer segments matter before prediction.
Sprint 2 | Engineered dataset, logistic-regression baseline, initial probability, risk level, and observed risk-factor table. | It delivers the core prioritization feature without requiring a complete deployed application. | The retention team can review a ranked customer list and give early feedback on thresholds, fields, and explanations.

## Sprint_Plan
Sprint | Goal | Activities | Deliverables | Changes Introduced | Feedback Received | Improvement Made
Sprint 1 - Data Foundation | Deliver a reliable and understandable data foundation. | Acquire data; validate fields; clean values; flag duplicate IDs; create summaries and exploratory charts. | Cleaned dataset; data dictionary; quality report; charts; Sprint 1 findings. | Raw data converted into a documented, reviewable dataset. | TO BE COMPLETED after the Sprint 1 review. | TO BE COMPLETED after feedback is implemented in Sprint 2.
Sprint 2 - Prediction MVP | Create the first customer-level churn-risk output. | Engineer simple features; train logistic regression; generate probabilities and risk categories. | Enhanced dataset; baseline metrics; initial prediction table; high-risk customer CSV. | Segment-level analysis refined into customer-level risk prioritization. | TO BE COMPLETED after the Sprint 2 review. | TO BE COMPLETED after feedback is implemented in Sprint 3.
Sprint 3 - Evaluation and Prototype | Test, explain, and refine the predictive MVP. | Compare models; perform cross-validation; test thresholds; create importance evidence; generate Streamlit prototype. | Model comparison; confusion matrices; refined risk table; prototype files; export function. | Baseline predictions refined using model comparison, evaluation evidence, and clearer risk explanation. | TO BE COMPLETED after the Sprint 3 review. | TO BE COMPLETED after feedback is implemented in Sprint 4.
Sprint 4 - Deployment Planning | Prepare a responsible deployment and monitoring proposal. | Design architecture; create tests and CI workflow; define monitoring, access, refresh, and ownership. | Deployment diagram; Streamlit app; requirements; tests; GitHub Actions workflow; monitoring plan. | The analytical prototype is packaged as a reproducible, testable deployment concept. | TO BE COMPLETED after the Sprint 4 or final review. | Record final recommendations and future backlog items.

## Feedback_Log
Sprint | Reviewer and Role | Feedback Received | Backlog Change | Improvement Completed | Evidence Location
Sprint 1
Sprint 2
Sprint 3
Sprint 4

## Definition_of_Done
Definition of Done
The output can be opened or demonstrated.
Cleaning or modelling steps are documented.
Required acceptance criteria are present.
Charts contain titles and readable labels.
Results have been reviewed by another team member.
The file is stored in the correct sprint folder.
Any stakeholder feedback is recorded.
No metric is claimed unless it was calculated.

## Deployment_Plan
Deployment Element | Proposal
Application Type | Internal Streamlit web application proof of concept.
Intended Users | Retention Manager; Service Supervisor; approved Business Managers; Data Science Team.
Data Refresh | Proposed weekly batch scoring using the latest authorized customer file.
Model Platform | scikit-learn pipeline saved with joblib.
Version Control | GitHub repository with reproducible source files.
Automated Validation | pytest tests executed by GitHub Actions.
Hosting Option | Private organizational server or private cloud environment.
Access Control | Restricted to authorized staff; customer IDs masked in the interface.
Monitoring | Data quality, prediction distribution, recall, precision, job success, and potential drift.
Deployment Status | Conceptual only; actual organizational deployment is not required for the assignment.

## Reflection
Reflection Area | Reflection
How Agile Helped | Agile divided an uncertain data science problem into small, reviewable outputs. Sprint 1 delivered reliable data, Sprint 2 delivered an initial predictive MVP, Sprint 3 tested and refined it, and Sprint 4 prepared a deployment concept.
How Feedback Improved the MVP | Complete this section using actual review feedback. Explain which requested change was converted into a backlog item and how it changed the following sprint output.
Challenges Encountered | Likely challenges include blank charge values, categorical encoding, class imbalance, threshold selection, false alerts, scope control, and the lack of live organizational users or data.